## Test task
План работ
1. Story Points для выполнение тестового задания
Story Points | Story |  | Сложность задачи | Эстимейт (часы) | Реально потратил времени (часы)
1 | File Processor can receive file in next format: CSV file format example: - Header row: field names - Data rows: timeseries data microseconds, value) |  |  | 16 | 8
| File Processor listening on new file available Transforming of original data format to REST endpoint payload |  |  | 20 | 4
2 | Each significant operations (for ex.: starting/ending of file processing) should be indicated as event in the workflow to notify subscribers. Timeseries data should be sent and received through Kafka data topics for further asynchronous processing. Each message should contain 1 or max 100 timeseries values. Events should be send as single messages through Kafka notification topic. |  |  | 40 | 16
3 | TimeSeries service can do next: 1) Listening of New Data File Processing event and keep in Event DB 2) Listening of data messages to be kept in Timeseries DB 3) Listening of Data File Processed event and keep in Event DB 4) Publishing of Timeseries Ready event when all messages of given file are kept in DB and ready for statistic calculation. Keep 5) Listening of New Data File Processing event and keep in Event DB 6) Listening of data messages to be kept in Timeseries DB 7) Listening of Data File Processed event and keep in Event DB 8) Publishing of Timeseries Ready event when all messages of given file are kept in DB and ready for statistic calculation. Keep event in Event DB |  |  | 40 | 16
4 | As a user I can have an access to REST endpoint to return aggregated statistic about processed data: 1) How many messages per file processed for whole period 2) Max Temperature through all messages 3) Average Voltage through all messages 4) Listening of Timeseries Ready endpoint to run statistic recalculation |  |  | 30 | 16
5 | As a user Engineer I can have access only to GET raw timeseries data and GET statistic data |  |  | 8 | 8
| As a user Admin I can have access only to GET events |  |  | 8 | 8
2. Настройка среды разработки + изучение технологий
| Задача | Описание | Сложность задачи | Эстимейт (часы) | Реально потратил времени (часы)
1. | Настроить среду разработки | Использовать Java 11 + Gradle + последние версии библиотек |  | 4 | 6
2. | Поднять Докер контейнер | Разобраться с Докером. Поднять на локальной машине и научиться подключаться удаленно к контейнеру для дебага
2.1. | Разобраться с доккером изучить документацию |  |  | 16
2.2. | Поднять Докер контейнер |  |  | 8 | 2
2.3. | Разобраться как подключиться к контейнеру удаленно для дебага |  |  | 8
3. | Установить Postgress |  |  | 2 | 1
3.1. | Спроектировать базу данных | Создать базу данных + необходимые таблицы |  | 16
4. | Разобраться и установить Cassandra |  |  | 16 | 4
4.1. | Разобраться и установить Kafka |  |  | 24 | 16
5. | Разобраться с микросервисной архитектурой |  |  | 48 | 8
6. | Повторить Spring |  |  | 30